## 1. Product Overview
Item | Description
Product Name | CompliancePal
Product Vision/ Purpose | To empower Micro, Small, and Medium Enterprises (MSMEs) with an intelligent, automated, and reliable system that simplifies GST compliance and e-invoicing processes, reducing manual effort and ensuring accuracy.
Business Goals / Key Success factors | Our business goal is to simplify and automate GST compliance for MSMEs, while key success depends on accuracy, usability, AI reliability, and secure data handling.
Primary Stakeholders | The primary stakeholders include MSME owners, accountants, GST authorities, system administrators, and developers who interact with or benefit from the system.

## 2. Product Backlog
Epic | Epic Title | User Story ID | User Story/Requirement | Technical Requirements | Priority (MoSCoW) | Story Points | Status | Owner | 7 | Test Owner
| Major features | Mandatory | Mandatory |  |  | (optional) | Mandatory | Mandatory | Mandatory | Mandatory
E1 | User Authentication | US1 | As a user, I want to sign up using my email and OTP so that I can securely access my account. | Registration screen, Login screen, OTP generation & validation, Error handling | Must Have | 8 | To Do | Team Lead | Test signup, OTP validation, login success/failure | Ankitha
E2 | User Authentication | US2 | As a user, I want to log in securely so that I can access my dashboard. | Login API, Session management | Must Have | 8 | done | Backend Dev | Test login credentials & session | Ankitha
E3 | Dashboard | US3 | As a user, I want to view a dashboard with key analytics so that I can quickly understand my GST data. | Login screen | Must Have | 10 | done | Frontend Dev | Test dashboard loading & data accuracy | Ankitha
E4 | Excel Upload | US4 | As a user, I want to upload Excel files so that my invoice data can be processed automatically. | File upload, validation, parsing using pandas | Must Have | 9 | To do | Backend Dev | Test file upload & format validation | Ankitha
E5 | Reconciliation | US5 | As a user, I want GST data validation so that errors are detected before filing. | GSTIN validation, tax rules | Must Have | 8 | To do | Backend Dev | Test mismatch detection | Ankitha
E6 | GST Validation | US6 | As a user, I want AI-based suggestions so that I can correct errors easily. | ML model, anomaly detection | Must Have | 12 | Done | Frontend Dev | Test GSTIN & tax calculation | Ankitha
E7 | AI Suggestions | US7 | I want IRN generation | Mock API integration | Must Have | 8 | Done | Backend Dev | Test suggestions accuracy | Ankitha
E8 | E-Invoicing | US8 | As a user, I want the system to match invoices so that I can identify mismatches and missing entries. | Matching logic, duplicate detection | Should Have | 13 | To Do | Backend Dev | Test IRN generation | Ankitha
Notes: | MoSCoW
|  | Must Have | Critical requirements that are essential for the project's success and must be delivered.
|  | Should Have | Important requirements that are highly desirable but not vital; the project can still be delivered without them, but it would be less ideal.
|  | Could Have | "Nice-to-have" requirements that are less important and have a lower impact if they are not included.
|  | Won't Have | Requirements that are not being delivered in the current project or timeframe, but may be considered for future iterations.
Story Points
|  | Fibonacci | 0,1,1,2,3,5,8,13,21,34,….
|  | (Modified) | 0,1,1,2,3,5,8,13,20 (points decided based on a User Story's complexity, effort needed & riks)
Ends at 20. Rarely extended to 40 and 100 for very large tasks.

## 3. Roadmap
Release |  | Key Features | Dependencies | Demo Status
Llist Epic Names
v0.1 | 2026-03-27 | User authentication | None | On Track
v0.2 | 2026-04-03 | Document Scanning and Character Extraction | Requeries Model Traning | On Track
v0.3 | 2026-04-10 | Dashboard MVP | UI Upgrade | Planned
v0.4 | 2026-04-17 | Model Fine-Tuning | None | Planned
v0.5 | 2026-04-24 | GST Reconciliation Engine | Data Processing Module | Planned
v1.0 | 2026-05-01 | Full Compliance System | Integration of all modules | Planned
v1.1 | 2026-05-08 | Performance Optimization & UI Enhancements | User Feedback | Planned

## 4. Retrospective
Note: This is for the team to learn and improve. I have taught you in the class on Nov 4, 2025.
Ideally, the team should do this at the end of every release. How often you do , I leave it to you.
What Went Well | What Didn’t Go Well | Improvements / Action Items | Owner
Net time what will you do differently
Team collaboration was great | The model traning did not go well | Fine Tuning of the model must be done | Development Lead
Excel upload and parsing worked correctly | Issues with inconsistent Excel formats | Standardize input format and add validation checks | Backend Developer
Authentication module implemented smoothly | Delay in OTP integration | Use reliable OTP service API and test earlier | Backend Developer
Dashboard UI was user-friendly | Some UI alignment issues | Improve UI responsiveness and cross-device testing | Frontend Developer
Reconciliation logic detected most mismatches | Edge cases were not handled properly | Add more test cases and improve matching algorithm | Backend Developer
Good coordination between frontend & backend | Integration delays between modules | Plan integration earlier in sprint | Team Lead